## Slide 1: Leveraging Capabilities of AI for Transparency and Accountability in Tendering
Presenter: Joseph Gamba (Researcher)
Project Period: 29 Nov 2023 - 22 May 2025
PI: Dr Michael S. Mollel (PCCB)
Co-PI: Prof Baraka Maiseli (UDSM)

## Slide 2: Project Timeline and Current Phase
Phase 1 (Current): Data collection and processing (Nov 2023 - Feb 2024)
Phase 2: Data analysis and AI model development (Mar 2024 - Aug 2024)
Phase 3: Model testing and refinement (Sep 2024 - Dec 2024)
Phase 4: Deployment and evaluation (Jan 2025 - May 2025)
Status: In Phase 1 - Data collection and processing

## Slide 3: Data Collection Goals
Initial Objective: Collect a comprehensive dataset of corruption cases related to procurement
Adapted Objective: Collect any cases prosecuted by PCCB due to the limited availability of procurement-specific cases
Purpose: Train and fine-tune the machine learning model to identify irregularities in tender documents

## Slide 4: Unforeseen Challenges in Data Collection
Primary Challenge:
  Lack of digital data; most documents in hardcopy or handwritten format
Impact:
  Delayed progress in data collection
  Increased resource requirements for digitization
  Potential delay in subsequent project phases
Lesson Learned:
  Importance of digital preparedness and data management strategies in research

## Slide 5: Overcoming Data Collection Hurdles
PCCB Financial Support:
  Engaged staff across regions for scanning and digitizing documents
  Result: 1,400 case files collected and digitized
Adaptive Strategy:
  Broadened scope to include all PCCB-prosecuted cases
  Ensures a larger dataset for more robust AI model training

## Slide 6: Ensuring Data Privacy and Legal Compliance
Challenge:
  PCCB law requires anonymization before sharing data with partners (e.g., University of Dar es Salaam)
  Time-consuming process to convert 1,400 scanned files to typed format
Legal Implications:
  Strict adherence to data protection laws
  Maintaining confidentiality of sensitive information

## Slide 7: Efficient Data Processing While Ensuring Privacy
Secretarial Support:
  Budget allocation for 28 secretaries (1 per region)
  Cost: 33,600,000 TZS (40,000 TZS daily rate, 30 days)
Technological Solutions:
  Exploring automated tools for efficient conversion
  Ensuring tools comply with data privacy requirements
Timeline Adjustment:
  Reallocating timelines for subsequent activities to accommodate delays

## Slide 8: Strategic Financial Management
Original Plan:
  Equipment budget (AI machine): 71,000,000 TZS
Budget Optimization:
  Collaboration with the University of Dodoma for machine access
  Reallocation of 33,600,000 TZS to secretarial support
Result:
  Cost-effective solution without compromising project quality
  Demonstrates adaptability and resource optimization

## Slide 9: Operational Costs and Accountability
Online Meetings:
  6 meetings, 13 participants
  Budget: 3,700,000 TZS for internet bundles
  Cost-saving measure: Shifted from in-person to online meetings
Specialized Tasks:
  Two-day intensive session for file extraction: 170,000 TZS
  Quarterly report writing (PI and Co-PI): 2,000,000 TZS

## Slide 10: Financial Summary and Project Outlook
Financial Summary:
  Total Project Budget: 150,000,000 TZS
  First Quarter Disbursement: 88,678,289 TZS (59% of budget)
  First Quarter Expenditure: 9,805,000 TZS
  Cash Balance: 78,873,289 TZS
Next Steps:
  Complete file conversion and anonymization (Est. completion: June 2024)
  Proceed with data analysis and AI model development (Jun-Aug 2024)
  Continuous budget monitoring and adaptive planning
  Regular financial and technical reporting to COSTECH

## Slide 11: Financial Summary and Project Outlook
Project demonstrates fiscal responsibility, adaptability, and commitment to legal compliance
Strategic budget reallocations ensure project continuity despite challenges
On track for developing an AI-driven solution for transparency in tendering processes